## SB Squares Tasks
Task # | Subject | Type | Assigned To | Status | Files Changed
4 | Add admin Reset Game and Clear Player Picks functionality | Feature | team-lead-2 | Completed | app/game/[gameId]/admin/page.tsx
5 | Fix bug: Prevent Reveal Numbers when batch 2 picks are incomplete | Bug Fix | team-lead-2 | Completed | app/game/[gameId]/admin/page.tsx
6 | Fix misaligned Patriots header row - add missing spacer for vertical team label | Bug Fix | ui-dev | Completed | components/Grid.tsx
7 | Disable Force Start Batch 2 button until all batch 1 picks are complete | Enhancement | ui-dev | Completed | app/game/[gameId]/admin/page.tsx
8 | Show draft order lists for both batch 1 and batch 2 in admin screen | Enhancement | ui-dev | Completed | app/game/[gameId]/admin/page.tsx
9 | Redesign batch draft order as compact horizontal icon row | UI Redesign | ui-dev | Completed | app/game/[gameId]/admin/page.tsx
10 | Add compact horizontal draft icons to main game PickControls | Enhancement | ui-dev | Completed | components/PickControls.tsx
11 | Fix page jumping to top when user picks a square | Bug Fix | ui-dev | Completed | hooks/use-game.ts, app/game/[gameId]/page.tsx
12 | Enhance sliding number reveal animation - slower speed and bigger bolder digits | Enhancement | ui-dev | Completed | components/Grid.tsx, components/ui/sliding-number.tsx
13 | Add distinct styling to squares picked by the current user (self) in the grid | Enhancement | ui-dev | Completed | components/Grid.tsx, components/GridCell.tsx
14 | Fix grid team name font size, centering, and consistent spacing from grid | UI Fix | ui-dev | Completed | components/Grid.tsx
15 | Research NFL team logo URLs for ScoreBoard component | Research | backend-dev | Completed | N/A (research only)
16 | Add team logos to ScoreBoard component (Google score card style) | Feature | ui-dev | Completed | components/ScoreBoard.tsx, components/TeamLogo.tsx
17 | Fix logo placement: logos beside team names in ScoreBoard and add logos to grid axis titles | UI Fix | ui-dev | Completed | components/ScoreBoard.tsx, components/Grid.tsx
19 | Prepare deployment readiness: gather all info and steps for Vercel + Supabase hosted production | DevOps | devops | Completed | N/A (documentation)
20 | Create .gitignore file for SBSquares project | DevOps | team-lead-2 | Completed | .gitignore
21 | Update next.config.ts with images.remotePatterns for ESPN CDN | Config | team-lead-2 | Completed | next.config.ts
22 | Show runner-up alongside winner in admin Score Entry card | Enhancement | ui-dev | Completed | app/game/[gameId]/admin/page.tsx
23 | Show quarter label (Q1/Q2/Q3/Q4) on winning and runner-up squares in the grid | Enhancement | ui-dev | Completed | components/Grid.tsx, components/GridCell.tsx
24 | Add ability to edit/correct submitted quarter scores and recalculate winners | Feature | ui-dev | Completed | app/game/[gameId]/admin/page.tsx
25 | Restore trophy icon on winning squares alongside the quarter label badge | Bug Fix | ui-dev | Completed | components/GridCell.tsx
26 | Add per-quarter score reset button in admin Score Entry | Feature | ui-dev | Completed | app/game/[gameId]/admin/page.tsx
27 | Add bottom padding/margin to grid so winner ring is not clipped | Bug Fix | ui-dev | Completed | components/Grid.tsx
28 | Add admin ability to edit player names and PINs | Feature | ui-dev | Completed | lib/types.ts, app/game/[gameId]/admin/page.tsx
29 | Add admin ability to edit the game code | Feature | ui-dev | Completed | app/game/[gameId]/admin/page.tsx
30 | Research: Can the current architecture support multiple games with separate user bases? | Research | backend-dev | Completed | N/A (research only)
32 | Add admin promote/demote toggle for secondary admins | Feature | ui-dev | Completed | app/game/[gameId]/admin/page.tsx
33 | Add Create Game flow on the landing page | Feature | ui-dev | Completed | app/page.tsx
34 | Add admin ability to add and remove players from a game | Feature | ui-dev | Completed | app/game/[gameId]/admin/page.tsx
35 | Add players table to realtime subscription in use-realtime.ts | Bug Fix | team-lead-2 | Completed | hooks/use-realtime.ts
36 | Verify Reset Game and admin actions scoped per game in multi-game | Research | backend-dev | Completed | N/A (research only)
37 | Research NFL team color schemes for dynamic theming | Research | backend-dev | Completed | N/A (research only)
38 | Add dark/light theme toggle and team-based color theming | Feature | ui-dev | Completed | app/globals.css, hooks/use-theme.ts, app/layout.tsx, app/game/[gameId]/page.tsx
39 | Provide step-by-step manual instructions for Supabase hosted project setup | DevOps | backend-dev | Completed | N/A (documentation)
40 | Set up CI/CD: git repo, GitHub remote, Vercel auto-deploy on push to main | DevOps | devops + team-lead-2 | Completed | .gitignore, GitHub repo, Vercel project
41 | Add admin ability to edit team names with safety checks | Feature | ui-dev | Completed | app/game/[gameId]/admin/page.tsx
43 | Create Help / How to Play page at /help | Feature | ui-dev | Completed | app/help/page.tsx, app/page.tsx, app/game/[gameId]/page.tsx
44 | Sliding number digits use theme/team primary color + deploy | Enhancement | team-lead-2 | Completed | components/Grid.tsx
45 | Add Google-style progress bar to scoreboard during live game | Enhancement | team-lead-2 | Completed | components/ScoreBoard.tsx, app/globals.css
46 | Fix manual pick progress bar overflow and incorrect count in PickControls | Bug Fix | ui-dev | Completed | components/PickControls.tsx
47 | Fix team name edit buttons hidden for non-setup game statuses in admin | Bug Fix | ui-dev | Completed | app/game/[gameId]/admin/page.tsx
49 | Architectural review and design for QR codes, configurable players/grid, and pricing | Architecture | architect | Completed | N/A (design document)
50 | Add post-login game rules modal with key points on game screen | Feature | ui-dev | Completed | app/game/[gameId]/page.tsx
51 | Finalize architecture design with user-confirmed decisions and create implementation tasks | Architecture | architect | Completed | N/A (design document)
52 | Schema migration: add max_players, price_per_square, prize_split, winner_pct, invite_enabled | Feature | team-lead-2 | Completed | supabase/migrations/20250206000000_game_features.sql
53 | Update TypeScript types and core game logic for new features | Feature | backend-dev | Completed | lib/types.ts, lib/game-logic.ts
54 | Add game configuration settings to admin dashboard | Feature | ui-dev | Completed | app/game/[gameId]/admin/page.tsx
55 | Adapt draft flow for single-batch games (20/25 players) | Feature | ui-dev | Completed | app/game/[gameId]/admin/page.tsx, components/PickControls.tsx
56 | Create /join/[gameCode] self-registration page for QR onboarding | Feature | ui-dev | Completed | app/join/[gameCode]/page.tsx
57 | Add QR code display and invite management to admin dashboard | Feature | ui-dev | Completed | app/game/[gameId]/admin/page.tsx
59 | Update create game flow to include max_players and price_per_square | Feature | team-lead-2 | Completed | app/page.tsx
61 | Create UAT test plan for new features: configurable players, pricing, QR, single-batch draft | UAT | uat-tester | Completed | docs/uat-test-plan-new-features.md
62 | Write UAT test plan document for all 6 feature areas | UAT | uat-tester | Completed | docs/uat-test-plan-comprehensive.md
63 | Create UAT test plan for admin features: reset game, player management, score entry | UAT | uat-tester | Completed | docs/uat-test-plan-admin.md
64 | Create UAT test plan for game features: grid, draft, digit reveal, theming, login | UAT | uat-tester | Completed | docs/uat-test-plan-game.md
65 | Update UAT test cases with exact implementation details from source code | UAT | uat-tester | Completed | docs/uat-test-plan-*.md
66 | Backfill existing games with default values for new columns | Migration | team-lead-2 | Completed | supabase/migrations/20250206000001_backfill_game_defaults.sql
67 | Replace hardcoded dollar amounts with example language in help page and rules modal | Enhancement | ui-dev | Completed | app/help/page.tsx, app/game/[gameId]/page.tsx
68 | Production readiness review for new features | Review | backend-dev | Completed | N/A (review)
69 | Execute UAT testing session - 143 test cases, 100% pass rate | UAT | uat-tester | Completed | N/A (testing)
71 | Remove explicit Join/Enter buttons - auto-join when required input entered | Enhancement | ui-dev | Completed | app/page.tsx
72 | Fix missing invite_enabled column in games table schema cache | Bug Fix | backend-dev | Completed | Supabase SQL (ALTER TABLE + NOTIFY pgrst)
73 | Fix: Players can join via /join page after game leaves setup status | Bug Fix | architect + team-lead-2 | Completed | app/join/[gameCode]/page.tsx, app/game/[gameId]/admin/page.tsx
75 | Analyze mid-draft join bug and provide architectural recommendation | Architecture | architect | Completed | N/A (analysis)
76 | Fix: Missing admin confirmation when starting draft with fewer than max_players | Bug Fix | team-lead-2 | Completed | app/game/[gameId]/admin/page.tsx
77 | Fix: Player added mid-draft not included in draft order | Bug Fix | team-lead-2 | Completed | app/game/[gameId]/admin/page.tsx
80 | Fix: Reset Game should unlock max_players setting for reconfiguration | Bug Fix | team-lead-2 | Completed | app/game/[gameId]/admin/page.tsx
81 | Analyze Reset Game max_players lock bug and recommend fix | Architecture | architect | Completed | N/A (analysis)
88 | Research Supabase free tier limits and estimate game capacity | Research | backend-dev | Completed | docs/research-findings.md
89 | Research Vercel free tier limitations for Next.js hosting | Research | devops | Completed | docs/research-findings.md
90 | Assess need for super-admin screen to manage multiple games | Research | architect | Completed | docs/research-findings.md
91 | Determine required production DB actions for recent model changes | Research | backend-dev | Completed | docs/research-findings.md
93 | Move MD files from root to docs/ folder and document research findings | DevOps | team-lead | Completed | docs/research-findings.md, docs/ARCHITECTURE.md, docs/UX_ANALYSIS.md
94 | Design game limit and superadmin safeguards | Architecture | architect | Completed | N/A (design document)
95 | Add game creation limit (max 20) to landing page | Feature | ui-dev | Completed | app/page.tsx, lib/constants.ts
96 | Create superadmin PIN verification API route | Feature | ui-dev | Completed | app/api/superadmin/verify/route.ts, .env.local
97 | Build superadmin dashboard page | Feature | ui-dev | Completed | app/superadmin/page.tsx, lib/utils.ts
98 | Create dummy test data for game limit testing | Testing | ui-dev | Completed | N/A (test data)
99 | Verify cascade delete and game limit enforcement | Testing | architect | Completed | N/A (verification)
100 | Add QR code copy-to-clipboard and save-as-PNG buttons | Feature | orchestrator | Completed | app/game/[gameId]/admin/page.tsx
101 | Add README.md with project overview, ASCII art, and agent team writeup | Docs | orchestrator | Completed | README.md
102 | Add CLAUDE.md project guide for future Claude Code sessions | Docs | orchestrator | Completed | CLAUDE.md
103 | Fix grid horizontal scroll on mobile — viewport-calc responsive cells | UI Fix | orchestrator | Completed | components/Grid.tsx, components/GridCell.tsx
104 | Fix admin page flash of 'Admin access required' during load | Bug Fix | orchestrator | Completed | app/game/[gameId]/admin/page.tsx
105 | Add all 32 NFL teams master list to lib/constants.ts | Feature | ui-dev | Completed | lib/constants.ts
106 | Update TeamLogo.tsx to use NFL_TEAMS from constants (all 32 teams) | Enhancement | ui-dev | Completed | components/TeamLogo.tsx
107 | Add color palettes for all 32 NFL teams in use-theme.ts | Enhancement | ui-dev | Completed | hooks/use-theme.ts
108 | Design TeamCombobox UX specification | UX | ux-expert | Completed | N/A (design spec)
109 | Build TeamCombobox component with filtered dropdown and logo preview | Feature | team-lead-2 | Completed | components/TeamCombobox.tsx
110 | Replace team inputs in game creation form with TeamCombobox | Enhancement | team-lead-2 | Completed | app/page.tsx
111 | Replace team inputs in admin page with TeamCombobox | Enhancement | ui-dev | Completed | app/game/[gameId]/admin/page.tsx
112 | Add city field to NFL_TEAMS and city search in TeamCombobox | Enhancement | ui-dev | Completed | lib/constants.ts, components/TeamCombobox.tsx
113 | Prevent duplicate team selection (same team for row and col) | Bug Fix | orchestrator | Completed | app/page.tsx, app/game/[gameId]/admin/page.tsx
114 | Add auto_scores_enabled and espn_event_id columns to games table + update TypeScript types | Migration | ui-dev | Completed | supabase/migrations/20250207000000_live_scores.sql, lib/types.ts
115 | Build ESPN API client with scoreboard fetch, game parser, team finder, and team-axis matcher | Feature | ui-dev | Completed | lib/espn.ts
116 | Create live-scores API route with ESPN polling, score mapping, and Supabase upserts | Feature | ui-dev | Completed | app/api/live-scores/route.ts
117 | Create client-side polling hook with adaptive intervals (30s live, 60s idle) | Feature | ui-dev | Completed | hooks/use-live-scores.ts
118 | Add auto-update ESPN toggle, NFL status indicator, and disable manual inputs in ScoreEntry | Feature | ui-dev | Completed | app/game/[gameId]/admin/page.tsx
119 | Research NFL live score APIs (ESPN public scoreboard, no auth required) | Research | product-researcher | Completed | N/A (research only)
120 | Create architecture plan for live score auto-update feature (data flow, file list, edge cases) | Docs | architect | Completed | N/A (architecture plan)
121 | Add Super Bowl auto-detect endpoint using ESPN scoreboard date filtering and team matching | Feature | architect | Completed | app/api/live-scores/detect/route.ts, lib/espn.ts
122 | Fix ESPN fetchESPNScores to fallback to summary endpoint for historical games | Bugfix | team-lead-2 | Completed | lib/espn.ts
123 | Free tier safety analysis for live score polling (30s interval confirmed safe) | Research | architect | Completed | N/A (analysis only)
124 | Add live score polling free tier analysis to research findings doc | Docs | product-researcher | Completed | docs/research-findings.md
125 | Add Session 5 agent team success story to README | Docs | ui-dev | Completed | README.md
Completed: | 93
By Assignee
architect | 7/7 completed
architect + team-lead-2 | 1/1 completed
backend-dev | 10/10 completed
devops | 2/2 completed
devops + team-lead-2 | 1/1 completed
team-lead | 1/1 completed
team-lead-2 | 15/15 completed
uat-tester | 6/6 completed
ui-dev | 42/42 completed
orchestrator | 6/6 completed
ux-expert | 1/1 completed
By Type
Architecture | 5
Bug Fix | 15
Config | 1
DevOps | 5
Enhancement | 16
Feature | 26
Migration | 1
Research | 8
Review | 1
UAT | 6
UI Fix | 3
UI Redesign | 1
Testing | 2
Docs | 2
UX | 1
126 | QR code session redirect — redirect returning players to game view | Feature | ui-dev | Completed | app/join/[gameCode]/page.tsx
127 | Game code reminder toast after joining via QR | Feature | ui-dev | Completed | app/join/[gameCode]/page.tsx, app/game/[gameId]/page.tsx
128 | Redirect /join to /?code= when game not accepting players | Feature | ui-dev | Completed | app/join/[gameCode]/page.tsx, app/page.tsx
129 | Add system theme option with 3-segment toggle (dark/light/system) | Feature | architect | Completed | hooks/use-theme.ts, app/layout.tsx, app/game/[gameId]/page.tsx
130 | Improve grid cell border visibility in dark mode | Enhancement | architect | Completed | components/GridCell.tsx, components/Grid.tsx, lib/utils.ts
20 | feature | Floating bottom bar for tentative pick UI (PickControls manual mode redesign, info/warning toasts, grid padding) | ui-dev | complete
21 | bugfix | Replace pick toasts with modals (info toast firing repeatedly, 30s warning not prominent enough) | ui-dev | complete
145 | bugfix | Fix dot indicator count showing x/10 instead of x/5 - totalPicks was picksUsed+picksRemaining (double counting tentative picks), changed to picksRemaining only | ui-dev | Done
146 | bugfix | Fix timeout handler stale closure and over-filling - added handleTimeoutRef for latest closure, re-fetches fresh squares from DB instead of stale state, added Math.max(0,...) safety cap | ui-dev | Done
147 | bugfix | Add mutex lock (pickingRef) to handleTentativePick to prevent race condition from fast double-clicks | ui-dev | Done
131 | Enhanced grid cell visibility (solid borders, glow, thicker width for self-picks in dark mode) | Enhancement | ui-dev | Completed | components/GridCell.tsx
132 | Schema migration: add is_tentative and tentative_started_at columns for tentative picks | Feature | architect | Completed | supabase/schema.sql, supabase/migrations/20250208000000_tentative_picks.sql, lib/game-logic.ts, app/api/live-scores/route.ts
133 | Implement tentative pick logic with circular replacement queue and 2-min timer | Feature | ui-dev | Completed | app/game/[gameId]/page.tsx
134 | Update Grid and GridCell for tentative pick visual states (pulsing ring, pick number badges) | Feature | ui-dev | Completed | components/Grid.tsx, components/GridCell.tsx
135 | Update PickControls with confirm button, countdown timer, and floating bottom bar | Feature | ui-dev | Completed | components/PickControls.tsx
136 | Update admin page for tentative pick cleanup (pickOnBehalf, resetGame, clearPlayerPicks) | Feature | architect | Completed | app/game/[gameId]/admin/page.tsx
137 | Debug tentative picks failure - root cause: migration not applied to deployed DB | Bug Fix | architect + ui-dev | Completed | N/A (migration deployment)
138 | Fix maxPicks derivation using getDraftConfig instead of stale picks_remaining | Bug Fix | ui-dev | Completed | app/game/[gameId]/page.tsx, components/PickControls.tsx
139 | Build admin square reassign feature with mini-grid and player dropdown | Feature | architect | Completed | app/game/[gameId]/admin/page.tsx
140 | Add ref-based mutex to handleRandomPick to prevent double-fire race condition | Bug Fix | ui-dev | Completed | components/PickControls.tsx
158 | bugfix | Add ref-based mutex to handleRandomPick in PickControls to prevent double-fire via devtools bypass | ui-dev | Done
159 | feature | Live Score Pulsing Squares - DB migration (live_quarter_score JSONB column) | architect | Done
160 | feature | Live Score Pulsing Squares - CSS pulsing animations + ScoreBoard live display | uiux-expert | Done
161 | feature | Live Score Pulsing Squares - Grid/GridCell live winner/runner-up pulsing logic | ui-dev-1 | Done
162 | feature | Live Score Pulsing Squares - Simulation system (API + fixture + admin runner) | ui-dev-2 | Done
163 | bugfix | Live Score Pulsing Squares - Fix duplicate type in ScoreBoard, final review + build | team-lead | Done
164 | bugfix | Live pulsing: allow LIVE badge on squares that are already confirmed winners from earlier quarters | Srini | Done
165 | bugfix | Increase badge font sizes (winner/runner-up/LIVE/tentative) from 5-8px to 10px for mobile readability | Srini | Done
166 | feature | Gate simulation runner behind per-game simulation_enabled flag with superadmin toggle | Srini | Done
166 | docs | Create future plan document for server-side live score polling (pg_cron + pg_net) | Claude | Done
167 | docs | Create future plan document for Cloudflare Turnstile CAPTCHA on game creation | Claude | Done | docs/plan-turnstile-captcha.md
168 | bugfix | Fix draft pick race condition: serialize pickOnBehalf with promise queue, fetch fresh squares from DB, verify pick success counts, retry on contention, add queue/active UI indicators | ui-dev | Done
169 | feature | Add UX feedback for draft pick operations: picking banner with spinner above draft circles, toast notifications on success/failure, disable ALL pick buttons during any active operation | ui-dev | Done
168 | bugfix | Fix race condition in admin draft pick-on-behalf: promise queue + fresh DB reads + verify/retry + UI queue indicators | Team (architect, uiux-expert, ui-dev) | Done | app/game/[gameId]/admin/page.tsx